## Sheet1
Phase	Activity	Deliverable	Team A (Self)	Team B	Team C	Other Group	Tech Lead	Template Link	Template Name
RQA	Requirment Analysis	SRS	X					https://iqmskm.ultimatix.net/km/index.php/IQMS_Templates	SRS Template for OOAD
	SRS IQA	IQA Doc				X		https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	SRS EQA	EQA Doc					X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	SRS Sign off	SRS				X
Design	HLD	Design Doc (Detailed Business Level)	X
	Design Doc IQA	IQA Doc				X		https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	Design Doc EQA	EQA Doc					X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	Design Doc Sign off	Design Doc (Detailed Business Level)				X
	Prepare FTS (Funcional Test Scenarios)	FTS		X
	FTS IQA	IQA Doc				X		https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	FTS EQA	EQA Doc					X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	FTS sign Off	FTS				X
Construction & Unit Testing	Coding	Code	X
	Prepare UTS/UTR	UTR	X
	Walkthourgh	IQA Doc	X					https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
Testing	Functional Testing	Deffect Log / FTR		X
	IQA FTR	IQA Doc				X
	Integration Testing	Deffect Log / ITR		X
	IQA ITR	IQA Doc				X
	FT Sign off	FTR				X	X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	IT Sign Off	FTR				X
Maintainance & Support	Impact Analysis	AID			X
	AID IQA	IQA Doc				X		https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	AID EQA	EQA Doc					X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	AID Sign Off	AID					X
	Coding	Code			X
	Functional Testing	FTR / Deffect Log			X
	FTR IQA	IQA Doc			X			https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	FTR EQA	EQA Doc				X	X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	Regression Testing	RTR / Deffect Log			X
	RTR IQA	IQA Doc				X		https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT
	RTR IQA	EQA Doc					X	https://iqmskm.ultimatix.net/km/index.php/IQMS_Forms	PF3030A REVIEW REPORT